**Bid format (To be submitted in PDF version)**

**State Consultant – CFS, Pedagogy, training and CCE**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Task/ Activity** | **Deliverables** | **Estimated deadline for completion of deliverable (please mention as day required and the month as per the TOR)** | **Estimated travel required for completion of deliverable (please mention destination/ number of days required as per the TOR)** | **Consultant’s proposal**  **Complete timeframe for deliverable** | **Consultants’ proposal**  **Cost (INR) (All inclusive i.e. professional fee, travel, DSA, communication, etc.)** |
| Support 100 Anandadayee Kakshas in the light of RTE | 1. Report on promotion of 100 Anandadayee Kakshas | 31 October 2015  80 days | 4 days  2 districts |  |  |
| Support strengthening of Child Cabinets in all elementary schools and upscaling Child Reporter programme in UP schools of all 24 districts. | 1. Training Module on Child Cabinets and Child Reporters 2. Report of state level orientation on child cabinets and child reporters | 31 October 2015  20 days |
| Support State Educational Support Mission (SESM) every month for quality improvement in schools | 1. Report of SESM visits every month with concrete suggestions and progress updates from all districts in each month. | 31 December 2015  10 days | 6 days  2 districts |  |  |
| Assist in Social Audit of all schools | 1. State report on Social Audit | 31 December 2015  30 days |
| Assist JCERT in textbook development – classes IV-V, and IX-X | 1. Draft textbooks for classes IV-V and IX-X are developed by December 2015 | 31 December 2015  30 days |
| Assist in AWP development – SSA, TE, MDMS and RMSA | 1. AWPs developed - SSA, TE, MDMS and RMSA for submission to MHRD, GoI | 29 February 2016  30 days | 6 days  3 districts |  |  |
| Support JEPC in development of Science centers in KGBVs and also monitoring of enrolment of girls from KGBVs. | 1. Report on support provided to JEPC in development of Science Centers in KGBVs 2. Report on monitoring of enrolment of girls from KGBVs | 29 February 2016  30 days |
| Assist in coordination of textbook related work – editing, layout, designing, illustration | 1. Development of final textbooks | 30 April 2016  60 days | 6 days  2 districts |  |  |
| Assist in module development for trainings under SSA, RMSA and TE | 1. Training modules developed under SSA, RMSA and TE | 30 April 2016  10 days |  |  |
| Assist in training and progress monitoring | 1. Report on each training | 30 June 2016  40 days | 7 days  4 districts |  |  |
| Document good practices – CCE, Social Audit, JRTEF, SESM, VCCA, etc. | 1. Submit documents of good practices | 30 June 2016  30 days |  |  |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| *Shaded area to be filled in by consultant* |  |  |  |  |  |
|  |  |  |  |  |  |
| **Name of the Bidder:** |  |  |  |  |  |
|  |  |  |  |  |  |
| **Address:** |  |  |  |  |  |
|  |  |  |  |  |  |
| **Contact no.:** |  |  |  |  |  |
|  |  |  |  |  |  |
| **Email address:** |  |  |  |  |  |
|  |  |  |  |  |  |
| **Date :** |  |  |  |  |  |