**Financial Bid**

**INDIVIDUAL CONSULTANT FOR STATE SBCC CONSULTANT- CSD March 2017- Dec 2017**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | **Major Tasks** | **Deliverable (s)** | **UNICEF Estimate** | | **Consultant's Proposal** | |
|  |  | **Estimated deadline for completion of deliverable** | **Estimated travel required for completion of deliverable (please mention number of days)** | **Complete timeframe for deliverable** | **Cost (INR)**  **(All inclusive i.e. professional fee, travel, DSA, communication, etc.)** |
|  | Coordination of 5 district level SBCC planning workshops across tribal districts | SBCC planning workshop document with workshop agenda, participant list and 5 Agreed District implementation plans | quarter 1 | 25 days |  |  |
|  | Participation and recommendation in quarterly review meetings for SBCC Task force at district level across 5 districts | Quarterly district SBCC review reports1,2,3 including minutes of the meeting and key recommendations across 5 districts ; one in each quarter | Quarter 1.2.3 | 15 days |  |  |
|  | Monitoring and supportive supervision through visits of 2 days per district across 5 districts, on a monthly basis in the field to grassroots level stakeholders | Consolidated monthly monitoring reports -1,2,3(one per quarter) | Quarter 1,2,3 | 45 days |  |  |
|  | Develop capacities of mid media partnerships (academia/ folk/ CBOs) to rollout localized mid media campaigns | consolidated Mid media actions plans of 5 districts | Quarter 2 | 10 days |  |  |
|  | Coordinate for refresher of DRGs on SBCC – CATS capacity cascade including experiential, class room based, and exchange visit based learning opportunities through final tribal module | **DRG capacity building report** | Quarter 1 | 15 days |  |  |
|  | Convergence meeting towards development of strategic framework of engagement of women based community networks defining roles, review indicators, norms, resource flow mechanisms, and authority & accountability framework. | GR at the district level with agreed engagement framework with Rajivika/ SHG networks (including clear communication on responsibility, accountability, capacity and accountability) | quarter 2 | 5 days |  |  |
|  | Organization of Convergence meet and consultation with NSS/NYKS and DIETS towards development of strategic framework of engagement of youth and children based community networks defining roles, review indicators, norms, resource flow mechanisms, and authority & accountability framework | GR at district Level with agreed engagement framework with NSS/NYKS and DIETS (including clear communication on responsibility, accountability, capacity and accountability) | quarter 2 | 5 Days |  |  |
|  | . Consultation with District, block and village level PRI representatives leading to development of strategic framework of engagement of PRIs defining roles, review indicators, norms, quality assurance and recognition | PRI engagement report with agreed engagement framework with PRI department (including clear communication on responsibility, accountability, capacity and accountability) | quarter 2 | 5 Days |  |  |
|  | Coordination with design agency towards finalization of multi stakeholder SBCC tool Kit after review of existing tools across Rajasthan and other neighboring states in the Rajasthan Context with special focus on tribal districts | Draft of multi stakeholder tool kit with key recommendations included | Quarter 1 | 0 Days |  |  |
|  | Facilitation of the documentation of Most Significant changes, processes and outcomes | experience sharing document of 5 districts with about 15 success stories of change | quarter 3 | 10 days |  |  |
|  | Provide SBCC orientation in ongoing capacity building programmes for district resource group and training institutions across 15days | consolidated report of Orientation agenda in multiple stakeholder capacity building programmes | quarter 3 | 15 Days |  |  |
|  | Organize state level Tribal consultation Dissemination of successful initiatives | Tribal consultation report with recommendations advocacy for upscale | quarter 3 | 5 Days |  |  |
|  |  |  |  |  |  |  |
|  | TOTAL AMOUNT IN RUPEES- | | | | | |

*Shaded area to be filled in by consultant*

**Name of the Bidder:**

**Address:**

**Contact no.:**

**Email address:**

**Date:**